# 1. Delivery strategy

The 24-week plan builds a demonstrable, safe academic platform in dependency order. Each phase ends with an exit gate: a reviewable artifact, automated checks, and a decision to proceed. The project retains a simulation boundary: no real emergency service is integrated or contacted.

Team roles: product/architecture lead, backend/data lead, frontend lead, ML/experimentation lead, QA/DevOps lead. One student may hold multiple roles, but each deliverable has a named accountable owner.

Every sprint ends with a working increment, a test run, an updated risk register, and a documented architecture decision where a major choice changes.

# 2. Operating model and definition of done

Work uses short-lived feature branches and protected main. Each change is linked to an issue, reviewed by a peer, tested in CI, documented where user-visible, and deployed to staging before it is declared complete.

Definition of done: acceptance criteria met; unit/integration tests pass; lint/security checks pass; no secrets or production data committed; observability added; API/event migration documented; rollback known; reviewer approval recorded.

Code ownership: backend owns schemas/API/event contracts; ML owns data/model cards; frontend owns PWA accessibility; DevOps owns pipelines/IaC; QA owns acceptance evidence.

Issue templates: feature, defect, security finding, experiment, dataset intake, architecture decision, and operational incident.

| Phase | Weeks | Goal | Exit gate |
| --- | --- | --- | --- |
| 1. Foundations | 1-4 | Reproducible repo, local stack, standards | Fresh clone runs Compose and CI |
| 2. Core platform | 5-8 | Secure incident workflow and durable data | Audited incident lifecycle passes integration suite |
| 3. User experience | 9-12 | Operator and verifier PWAs | End-to-end task/evidence/decision demo |
| 4. ML intelligence | 13-16 | Perception, fusion and comparison | Reproducible evaluation and model cards |
| 5. TMVN and explainability | 17-20 | Tasking, escalation, operator control | Simulation demonstrates ambiguous-case loop |
| 6. Staging and review | 21-24 | Hardened AWS pilot and final evidence | Load/security/restore/review demo complete |

# 3. Phase 1 - Foundations (weeks 1-4)

Establish a monorepo with frontend, backend, ml-services, infra, docs and test directories. Compose runs PostgreSQL/PostGIS, Kafka, Neo4j, MinIO/S3-compatible storage, gateway and observability stubs. Create environment templates with secret names only, never values.

Week 1: backlog, architecture decision records, repository, contribution guide, branch protections.

Week 2: Compose, health checks, base Spring Boot/React/Python services, lint/format/test commands.

Week 3: Flyway migrations, mock-source generator, OpenAPI skeleton, Kafka topic convention, correlation IDs.

Week 4: GitHub Actions, SAST/dependency/container scans, staging baseline and walkthrough.

Acceptance: a new contributor can run the stack, create mock events, inspect logs and pass CI without manual database setup.

# 4. Phase 2 - Core platform (weeks 5-8)

Implement the system of record before advanced ML. The Incident Service owns lifecycle transitions; the Evidence Service owns upload policy; the Decision Service owns approval/override; the Audit Service appends immutable events. The gateway enforces OAuth2/JWT and RBAC.

Week 5: PostGIS incident/observation/confidence schema and indexes; Neo4j relationship model.

Week 6: Kafka producers/consumers, outbox, idempotency, retry and dead-letter processing.

Week 7: OAuth2/JWT, role matrix, audit events, upload presigning and validation.

Week 8: REST and event contract tests, API documentation, duplicate/replay and permission acceptance tests.

Acceptance: incident creation through approved decision can be replayed, traced, and denied correctly by role.

# 5. Phase 3 - User experience (weeks 9-12)

Build thin vertical slices first: the operator map reads mock incidents, opens an explanation, and records a decision; then the verifier PWA receives a task and submits evidence. Avoid building administration breadth before this core loop works.

Week 9: design system, sign-in, role routing, accessible map/list view.

Week 10: incident detail, evidence timeline, confidence explanation, approval/adjust/override flow.

Week 11: verifier task flow, permission/consent screen, location/evidence upload, offline draft.

Week 12: notifications, administration, responsive/accessibility tests, end-to-end Playwright suite.

Acceptance: demonstration completes operator review and verifier evidence flow on desktop and mobile viewport with keyboard support.

# 6. Phase 4 - ML intelligence (weeks 13-16)

ML work is reproducible and separated from online serving. Dataset intake records license and version. Event/location-based splits are created before feature engineering. MLflow or equivalent records parameters, metrics, artifacts, calibration plots and model cards.

Week 13: dataset manifests, preprocessing, label checks, leakage tests, baseline data pipeline.

Week 14: train YOLOv8-S/RT-DETR fire comparison and U-Net/DeepLabV3+ flood comparison.

Week 15: train DistilBERT/logistic NLP comparison; feature snapshots and calibrated XGBoost fusion baseline.

Week 16: PyMC Bayesian fusion, credible intervals, threshold policy, drift metrics, versioned inference API.

Acceptance: repeatable report compares models on held-out event groups; no model is deployed without calibration, model card and rollback artifact.

# 7. Phase 5 - TMVN, explainability and simulation (weeks 17-20)

The Trusted Mobile Verification Network is built as a simulated network with configurable verifier positions, reliability, availability, cost, travel time and response behaviour. The selection score is visible to operators and can be sensitivity-tested.

Week 17: OSMnx/NetworkX routing, SimPy scenario runner, verifier score and escalation rules.

Week 18: task creation, notification, expiry, re-assignment, evidence reliability and conflict handling.

Week 19: evidence fusion, signal contribution display, recommendation generator and audit-linked explanation.

Week 20: operator approval controls, simulated police/fire/ambulance/shelter dispatch planner, scenario tests.

Acceptance: low-risk, high-confidence, ambiguous, no-response, conflicting-evidence and override scenarios all produce correct states and audit records.

# 8. Phase 6 - AWS staging, assurance and review (weeks 21-24)

Infrastructure is deployed first to staging using least privilege and separate environment configuration. Production is only a documented target; final academic demonstration remains staging/simulated unless governance explicitly authorises a different environment.

Week 21: AWS VPC, ECS/Fargate, RDS, S3, Kafka, Secrets Manager, CloudWatch and IaC review.

Week 22: dashboards, SLO alerts, rate limiting, error tracking, backup and restore drill.

Week 23: security review, dependency remediation, load/chaos testing, cost review and accessibility testing.

Week 24: pilot scenarios, final metrics, review demo, user guide, architecture pack and retrospective.

Acceptance: staged release passes smoke/security/load/restore checks; dashboard shows health; rollback is rehearsed; review evidence is packaged.

# 9. Data governance, quality and evaluation

Dataset intake is blocked until license, attribution, purpose, personal-data risk, geographic applicability and storage location are recorded. Training data is versioned with checksums; samples with unclear rights or unsafe personal content are excluded. Evidence is never used for model retraining without explicit governance approval.

Quality targets: API contract coverage 100% for published endpoints; critical workflow end-to-end coverage; no unresolved critical/high security findings at release gate.

ML report: mAP/precision/recall/F1 for fire; IoU/Dice for flood; F1 for NLP; calibration/Brier/ECE, false dispatch rate, verification latency and cost for fusion.

Human review: operator overrides and post-scenario adjudication form the gold evaluation set; disagreement is retained as uncertainty, not silently relabelled.

# 10. Deployment, rollback and operational gates

CI creates immutable tagged images. CD deploys to staging, runs migrations using backward-compatible expand/contract changes, performs smoke and contract checks, then requires manual approval before any protected environment. Feature flags protect new fusion policies and UI actions.

Rollback: reverse traffic to last healthy image; disable a model through registry alias; pause a faulty consumer; preserve failed events in DLQ; use tested RDS point-in-time recovery only under incident command.

Release gates: passing CI, peer review, security scan, migration plan, observability, automated tests, staging smoke test, rollback confirmation, and accountable approver.

Monitoring gates: P95 latency, error rate, Kafka lag, source freshness, dead-letter count, upload failure, task expiry, override rate, model confidence distribution and calibration drift.

# 11. Risks and mitigations

The plan manages technical and academic risks early rather than leaving them to final integration.

| Risk | Mitigation | Owner |
| --- | --- | --- |
| Dataset license/availability changes | Intake checklist, mirrors only when permitted, maintain secondary candidates | ML lead |
| Model overconfidence or leakage | Event-grouped splits, calibration, operator approval, model cards | ML lead |
| Complex integration delays | Vertical slice first, mocks/adapters, contract tests | Architecture lead |
| Evidence privacy/security | Short-lived URLs, RBAC, encryption, upload scanning, audit | Backend/DevOps |
| Cloud cost growth | Budgets, autoscaling caps, staging schedules, cost dashboard | DevOps |
| Verifier non-response | Simulation, timeout/escalation, fallback operator review | Product lead |

# 12. Requirements traceability and review milestones

The traceability matrix is maintained in the repository and updated every sprint. It links each objective to component, test evidence, and review demonstration. Review 1 demonstrates foundations plus early perception dataset/model work; Review 2 demonstrates the full human verification loop; final review demonstrates evaluation, security, resilience and a controlled pilot.

| Requirement | Component | Verification evidence | Review |
| --- | --- | --- | --- |
| Multi-source confidence | Adapters + Fusion Service | Event replay + calibration report | R2/Final |
| Cost/reliability-aware TMVN | Selection + Simulator | Scenario comparison | R2/Final |
| Explainable human approval | Decision + Audit + Operator PWA | E2E approve/override trace | R2/Final |
| Reliable platform operations | AWS + CI/CD + Monitoring | Load, restore and alert evidence | Final |

# 13. Final assumptions

AWS is the target cloud; responsive PWAs are the user channels; dispatches are simulated or operator-approved academic demonstrations; and external data is conditional on current rights and institutional approval. These constraints are design safeguards, not temporary omissions.